## North Bandai Activity Progress
Comp. no. | Farm Name | Area (Ha) | Activity | Avg. Md/Ha | Total Md | Rate/Md | Total | Cost per Ha (GHS) | Cost per Ha (USD)
Compt 16 | North Bandai | 112.6 | Line Slashing | 4 | 450.4 | 54.63 | 24605.352 | 218.52 | 32.1353
Compt 17 | North Bandai | 38.5 | Line Slashing | 4 | 154 | 54.63 | 8413.02 | 218.52 | 32.1353
Compt 17 | North Bandai | 40 | Line Slashing | 3 | 120 | 54.63 | 6555.6 | 163.89 | 24.1015
Compt 10 | North Bandai | 35 | Slashing | 6 | 210 | 45.17 | 9485.7 | 271.02 | 39.8559
Compt 10 | North Bandai | 70.2 | Slashing | 6 | 421.2 | 54.63 | 23010.156 | 327.78 | 48.2029
Compt 16 | North Bandai | 26 | Slashing | 8 | 208 | 61.63 | 12819.04 | 493.04 | 72.5059
Compt 17 | North Bandai | 28 | Slashing | 8 | 224 | 61.63 | 13805.12 | 493.04 | 72.5059
Compt 18 | North Bandai | 44.5 | Slashing | 8 | 356 | 54.63 | 19448.28 | 437.04 | 64.2706
Compt 19 | North Bandai | 61.8 | Slashing | 8 | 494.4 | 54.63 | 27009.072 | 437.04 | 64.2706
Compt 9 | North Bandai | 13 | Slashing | 6 | 78 | 54.63 | 4261.14 | 327.78 | 48.2029
Compt 9 | North Bandai | 115 | Slashing | 6 | 690 | 54.63 | 37694.7 | 327.78 | 48.2029
| Total Ha | 584.6 | 116.9% | 6.0909 | 3406 |  | Avg. Cost of Activity | Avg. Cost USD | 49.6718 | % shown is the % completed.
Compt 10 | North Bandai | 57 | Marking | 1.5 | 313.5 | 61.63 | 19321.005 | 92.445 | 13.5949
Compt 17 | North Bandai | 96 | Marking | 3 | 768 | 61.63 | 47331.84 | 184.89 | 27.1897
Compt 19 | North Bandai | 56 | Marking | 3 | 448 | 61.63 | 27610.24 | 184.89 | 27.1897
Compt 16 | North Bandai | 70 | Marking | 3 | 560 | 61.63 | 34512.8 | 184.89 | 27.1897
Compt 16 | North Bandai | 31 | Marking | 3 | 248 | 61.63 | 15284.24 | 184.89 | 27.1897
Compt 18 | North Bandai | 40 | Marking | 3 | 320 | 61.63 | 19721.6 | 184.89 | 27.1897
Compt 9 | North Bandai | 41 | Marking | 1.5 | 225.5 | 58.17 | 13117.335 | 87.255 | 12.8316
| Total Ha | 391 | 78.2% | 2.5714 | 2883 |  |  | Avg. Cost USD | 26.5058 | % shown is the % completed.
Compt 10 | North Bandai | 57 | Pitting | 4 | 313.5 | 61.63 | 19321.005 | 246.52 | 36.2529
Compt 17 | North Bandai | 96 | Pitting | 5 | 768 | 61.63 | 47331.84 | 308.15 | 45.3162
Compt 19 | North Bandai | 56 | Pitting | 5 | 448 | 61.63 | 27610.24 | 308.15 | 45.3162
Compt 16 | North Bandai | 70 | Pitting | 5 | 560 | 61.63 | 34512.8 | 308.15 | 45.3162
Compt 16 | North Bandai | 31 | Pitting | 5 | 248 | 61.63 | 15284.24 | 308.15 | 45.3162
Compt 18 | North Bandai | 40 | Pitting | 5 | 320 | 61.63 | 19721.6 | 308.15 | 45.3162
Compt 9 | North Bandai | 41 | Pitting | 4 | 225.5 | 58.17 | 13117.335 | 232.68 | 34.2176
| Total Ha | 391 | 78.2% | 4.7143 | 2883 |  |  | Avg. Cost USD | 40.4447 | % shown is the % completed.
Compt 16 | North Bandai | 45 | Broadcast spray | 2.5 | 112.5 | 61.63 | 6933.375 | 154.075 | 22.6581
Compt 16 | North Bandai | 67 | Broadcast spray | 2.5 | 167.5 | 61.63 | 10323.025 | 154.075 | 22.6581
Compt 18 | North Bandai | 40 | Broadcast spray | 2.5 | 100 | 61.63 | 6163 | 154.075 | 22.6581
Compt 19 | North Bandai | 56 | Broadcast spray | 2.5 | 140 | 61.63 | 8628.2 | 154.075 | 22.6581
| Total Ha | 208 | 41.6% | 2.5 | 520 |  |  | Avg. Cost USD | 31.7587 | % shown is the % completed.
Compt 16 | North Bandai | 102 | Planting | 5 | 510 | 61.63 | 31431.3 | 308.15 | 45.3162
Compt 18 | North Bandai | 20 | Planting | 5 | 100 | 61.63 | 6163 | 308.15 | 45.3162
Compt 19 | North Bandai | 60 | Planting | 5 | 300 | 61.63 | 18489 | 308.15 | 45.3162
| Total Ha | 182 | 36.4% | 5 | 910 |  |  | Avg. Cost USD | 34.8612 | % shown is the % completed.
Compt 16 | North Bandai | 60 | Post Planting Casing | 3 | 180 | 61.63 | 11093.4 | 184.89 | 27.1897
Compt 19 | North Bandai | 60 | Post Planting Casing | 3 | 180 | 61.63 | 11093.4 | 184.89 | 27.1897
| Total Ha | 120 | 24% | 3 | 360 |  |  | Avg. Cost USD | 31.5982 | % shown is the % completed.
|  |  | Total Man Days per Ha | 23.8766 | Avg. Rate/ Md | 59.2953 |  | Avg. Cost / Ha USD | 214.8404
Notes:
(1) When doing the progress visual, you should order the activities as above Line slashing / Slashing then Marking & Pitting then broadcast spray then planting then post planting casing. This is because this is the order these activities occur in the field.
(2) Line slashing and slashing should be grouped.
(3) All activities are out of a total of 500 ha as that's the target planting area. The reason that slashing / line slashing is more is because we needed to clear a larger area in gross ha to get our net planting area (as 1 ha for us is 500 plants and not how many plants can fit in 1 ha as we leave space for standing trees)
(4) Stacking was a once off activity and not something widely used so this won't be shown on the activity progress visual. Therefore this information is on the dataset but removed here.

## Bandai Hills Activity Progress
Comp. no. | Farm Name | Area (Ha) | Activity | Avg. Md/Ha | Total Md | Rate/Md | Total | Cost per Ha (GHS) | Cost per Ha (USD)
Compt 48 | Bandai Hills | 115 | Line Slashing | 3 | 345 | 51.15 | 17646.75 | 153.45 | 22.5662
Compt 48 | Bandai Hills | 16.7 | Line Slashing | 3 | 50.1 | 51.15 | 2562.615 | 153.45 | 22.5662
Compt 49 | Bandai Hills | 62 | Line Slashing | 3 | 186 | 51.15 | 9513.9 | 153.45 | 22.5662
Compt 49 | Bandai Hills | 42 | Line Slashing | 4 | 168 | 58.17 | 9772.56 | 232.68 | 34.2176
Compt 49 | Bandai Hills | 40 | Line Slashing | 4 | 160 | 58.17 | 9307.2 | 232.68 | 34.2176
Compt 106 | Bandai Hills | 45 | Slashing | 8 | 360 | 58.17 | 20941.2 | 465.36 | 68.4353
Compt 106 | Bandai Hills | 55 | Slashing | 8 | 440 | 58.17 | 25594.8 | 465.36 | 68.4353
Compt 119 | Bandai Hills | 52 | Slashing | 8 | 416 | 58.17 | 24198.72 | 465.36 | 68.4353
Compt 119 | Bandai Hills | 78.23 | Slashing | 8 | 625.84 | 58.17 | 36405.1128 | 465.36 | 68.4353
Compt 49 | Bandai Hills | 5.3 | Slashing | 8 | 42.4 | 58.17 | 2466.408 | 465.36 | 68.4353
| Total Ha | 511.23 | 102.2% | 5.7 | 2793.34 |  |  | Avg. Cost USD | 47.831 | % shown is the % completed.
Compt 48 | Bandai Hills | 20 | Marking | 3 | 160 | 58.17 | 9307.2 | 174.51 | 25.6632
Compt 49 | Bandai Hills | 65 | Marking | 3 | 520 | 58.17 | 30248.4 | 174.51 | 25.6632
Compt 106 | Bandai Hills | 35 | Marking | 3 | 280 | 58.17 | 16287.6 | 174.51 | 25.6632
Compt 106 | Bandai Hills | 65 | Marking | 3 | 520 | 58.17 | 30248.4 | 174.51 | 25.6632
Compt 119 | Bandai Hills | 52.08 | Marking | 3 | 416.64 | 58.17 | 24235.9488 | 174.51 | 25.6632
Compt 119 | Bandai Hills | 78.15 | Marking | 3 | 625.2 | 58.17 | 36367.884 | 174.51 | 25.6632
Compt 48 | Bandai Hills | 37.2 | Marking | 3 | 297.6 | 58.17 | 17311.392 | 174.51 | 25.6632
Compt 48 | Bandai Hills | 84.8 | Marking | 3 | 678.4 | 58.17 | 39462.528 | 174.51 | 25.6632
| Total Ha | 437.23 | 87.45% | 3 | 3497.84 |  |  | Avg. Cost USD | 25.6632 | % shown is the % completed.
Compt 48 | Bandai Hills | 20 | Pitting | 5 | 160 | 58.17 | 9307.2 | 290.85 | 42.7721
Compt 49 | Bandai Hills | 65 | Pitting | 5 | 520 | 58.17 | 30248.4 | 290.85 | 42.7721
Compt 106 | Bandai Hills | 35 | Pitting | 5 | 280 | 58.17 | 16287.6 | 290.85 | 42.7721
Compt 106 | Bandai Hills | 65 | Pitting | 5 | 520 | 58.17 | 30248.4 | 290.85 | 42.7721
Compt 119 | Bandai Hills | 52.08 | Pitting | 5 | 416.64 | 58.17 | 24235.9488 | 290.85 | 42.7721
Compt 119 | Bandai Hills | 78.15 | Pitting | 5 | 625.2 | 58.17 | 36367.884 | 290.85 | 42.7721
Compt 48 | Bandai Hills | 37.2 | Pitting | 5 | 297.6 | 58.17 | 17311.392 | 290.85 | 42.7721
Compt 48 | Bandai Hills | 84.8 | Pitting | 5 | 678.4 | 58.17 | 39462.528 | 290.85 | 42.7721
| Total Ha | 437.23 | 87.45% | 5 | 3497.84 |  |  | Avg. Cost USD | 42.7721 | % shown is the % completed.
Compt 119 | Bandai Hills | 80 | Broadcast spray | 2.5 | 200 | 58.17 | 11634 | 145.425 | 21.386
Compt 48 | Bandai Hills | 72 | Broadcast spray | 2.5 | 180 | 58.17 | 10470.6 | 145.425 | 21.386
Compt 48 | Bandai Hills | 68 | Broadcast spray | 2.5 | 170 | 58.17 | 9888.9 | 145.425 | 21.386
Compt 48 | Bandai Hills | 30 | Broadcast spray | 2.5 | 75 | 58.17 | 4362.75 | 145.425 | 21.386
Compt 49 | Bandai Hills | 50 | Broadcast spray | 2.5 | 125 | 58.17 | 7271.25 | 145.425 | 21.386
| Total Ha | 300 | 60% | 2.5 | 750 |  |  | Avg. Cost USD | 21.386 | % shown is the % completed.
Compt 119 | Bandai Hills | 40 | Planting | 5 | 200 | 58.17 | 11634 | 290.85 | 42.7721
Compt 48 | Bandai Hills | 20 | Planting | 4 | 80 | 58.17 | 4653.6 | 232.68 | 34.2176
Compt 48 | Bandai Hills | 120 | Planting | 5 | 600 | 58.17 | 34902 | 290.85 | 42.7721
Compt 49 | Bandai Hills | 20 | Planting | 5 | 100 | 58.17 | 5817 | 290.85 | 42.7721
| Total Ha | 200 | 40% | 4.75 | 980 |  |  | Avg. Cost USD | 40.6335 | % shown is the % completed.
Compt 48 | Bandai Hills | 45 | Post Planting Casing | 3 | 135 | 58.17 | 7852.95 | 174.51 | 25.6632
| Total Ha | 45 | 9% | 3 | 135 |  |  | Avg. Cost USD | 25.6632 | % shown is the % completed.
Compt 48 | Bandai Hills | 30 | Mulching | 2 | 60 | 58.17 | 3490.2 | 116.34 | 17.1088
| Total Ha | 30 | 6% | 2 | 60 |  |  | Avg. Cost USD | 17.1088 | % shown is the % completed.
|  |  | Total Man Days per Ha | 25.95 | Avg. Cost / Ha USD | 57.6008 |  | Avg. Cost / Ha USD | 221.0579
Notes:
(1) When doing the progress visual, you should order the activities as above Line slashing / Slashing then Marking & Pitting then broadcast spray then planting then post planting casing then post planting mulching. This is because this is the order these activities occur in the field.
(2) Line slashing and slashing should be grouped.
(3) All activities are out of a total of 500 ha as that's the target planting area. The reason that slashing / line slashing is more is because we needed to clear a larger area in gross ha to get our net planting area (as 1 ha for us is 500 plants and not how many plants can fit in 1 ha as we leave space for standing trees)
(4) Stacking was a once off activity and not something widely used so this won't be shown on the activity progress visual
(5) USD exchange rate is GHS 6.8: $1, which his the current average exchange rate from Jan - June.

## Lanao Bamboo Activity Progress
Comp. no. | Farm Name | Area (Ha) | Activity | Md/Ha | Total Md | Rate/Md | Total | Cost per Ha (PHP) | Cost per Ha (USD)
| Lanao - Bamboo | 297.28 | Slashing | 12.3789 | 3680 | 319 | 1173920 | 3948.8698 | 75.794
| Total Ha | 297.28 | 29.73% | 12.3789 |  |  |  | Avg. Cost USD | 75.794 | % shown is the % completed.
| Lanao - Bamboo | 229.85 | Marking | 1.2251 | 281.6 | 319 | 89830.4 | 390.8218 | 7.5014
| Total Ha | 229.85 | 22.98% | 1.2251 |  |  |  | Avg. Cost USD | 7.5014 | % shown is the % completed.
| Lanao - Bamboo | 47.61 | Pitting | 3.1233 | 148.7 | 319 | 47435.3 | 996.3306 | 19.1234
| Total Ha | 47.61 | 4.761% | 3.1233 |  |  |  | Avg. Cost USD | 19.1234 | % shown is the % completed.
| Lanao - Bamboo | 26.7 | Broadcast spray | 2.3262 | 62.11 | 319 | 19813.09 | 742.0633 | 14.2431
| Total Ha | 26.7 | 2.67% | 2.3262 |  |  |  | Avg. Cost USD | 14.2431 | % shown is the % completed.
| Lanao - Bamboo | 39.95 | Planting | 2.5282 | 101 | 319 | 32219 | 806.4831 | 15.4795
| Lanao - Bamboo | 58 | Planting (Seedling Hauling) | 1.2414 | 72 | 319 | 22968 | 396 | 7.6008
| Total Ha | 39.95 | 3.995% | 3.7695 |  |  |  | Avg. Cost USD | 23.0803 | % shown is the % completed.
| Lanao - Bamboo | 27.74 | Post Planting Casing | 1.8025 | 50 | 319 | 15950 | 574.982 | 11.0361
| Total Ha | 27.74 | 2.774% | 1.8025 |  |  |  | Avg. Cost USD | 11.0361 | % shown is the % completed.
|  |  | Total Man Days per Ha | 24.6256 | Avg. Rate/Md | 319 |  | Avg. Cost / Ha USD | 150.7783
Notes:
(1) When doing the progress visual, you should order the activities as above Line slashing / Slashing then Marking & Pitting then broadcast spray then planting then post planting casing then post planting mulching. This is because this is the order these activities occur in the field.
(2) Line slashing and slashing should be grouped.
(3) All activities are out of a total of 500 ha as that's the target planting area. The reason that slashing / line slashing is more is because we needed to clear a larger area in gross ha to get our net planting area (as 1 ha for us is 500 plants and not how many plants can fit in 1 ha as we leave space for standing trees)
(4) Stacking was a once off activity and not something widely used so this won't be shown on the activity progress visual
(5) USD exchange rate is GHS 6.8: $1, which his the current average exchange rate from Jan - June.

## Lanao Trees Activity Progress
Comp. no. | Farm Name | Area (Ha) | Activity | Avg. Md/Ha | Total Md | Rate/Md | Total | Cost per Ha (PHP) | Cost per Ha (USD)
| Lanao - Trees | 19.9 | Slashing | 9.397 | 187 | 319 | 59653 | 2997.6382 | 57.5362
| Lanao - Trees | 17.33 | Marking | 2.7121 | 47 | 319 | 14993 | 865.1471 | 16.6055
| Lanao - Trees | 14.52 | Pitting | 3.2493 | 47.18 | 319 | 15050.42 | 1036.5303 | 19.895
| Lanao - Trees | 15.15 | Planting | 2.5083 | 38 | 319 | 12122 | 800.132 | 15.3576
| Lanao - Trees | 34 | Planting (Seedling Hauling) | 1.0294 | 35 | 319 | 11165 | 328.3824 | 6.3029
| Lanao - Bamboo | 297.28 | Slashing | 12.3789 | 3680 | 319 | 1173920 | 3948.8698 | 75.794
| Lanao - Bamboo | 229.85 | Marking | 1.2251 | 281.6 | 319 | 89830.4 | 390.8218 | 7.5014
| Lanao - Bamboo | 47.61 | Pitting | 3.1233 | 148.7 | 319 | 47435.3 | 996.3306 | 19.1234
| Lanao - Bamboo | 26.7 | Broadcast spray | 2.3262 | 62.11 | 319 | 19813.09 | 742.0633 | 14.2431
| Lanao - Bamboo | 39.95 | Planting | 2.5282 | 101 | 319 | 32219 | 806.4831 | 15.4795
| Lanao - Bamboo | 58 | Planting (Seedling Hauling) | 1.2414 | 72 | 319 | 22968 | 396 | 7.6008
| Lanao - Bamboo | 27.74 | Post Planting Casing | 1.8025 | 50 | 319 | 15950 | 574.982 | 11.0361

## Total Cost per Planted Ha
BUDGET SUMMARY
| TOTAL (USD) | Cost per Ha (USD)
Ghana: Current Cost per Ha
Nursery Cost | 42191.1361 | 110.448
Cap-Ex | 188812.2228 | 494.2728
Infrastructure | 87814.0463 | 229.8797
Land Preparation | 177135.3004 | 463.705
Planting | 113089.9 | 296.0469
Replanting | 5046.967 | 13.212
Maintenance | 1822.4741 | 4.7709
Fire & Security | 5144.0907 | 13.4662
Impact | 1603.9428 | 4.1988
Administration | 84778.3144 | 221.9328
Tax | 0 | 0
Total WAI Jan - June Budget (USD) | 707438.3947 | 1851.933
| TOTAL (USD) | Cost per Ha (USD)
Philippines: Current Cost per Ha
Nursery Cost | 112603 | 2043.6116 | Based on actual nursery costs since we know this is over
Cap-Ex | 227726 | 4132.9583
Infrastructure | 33861 | 614.5372
Land Preparation | 112281.6852 | 2037.7801
Planting | 33618.4957 | 610.136
Replanting | 0 | 0
Maintenance | 389.1075 | 7.0618
Fire & Security | 192.7141 | 3.4975
Impact | 31993.129 | 580.6376
Administration | 100321.5161 | 1820.7172
Tax | 0 | 0
Total Lanao Bamboo Budget (USD) | 652986.6476 | 11850.9373
| Ghana | Philippines
Cost per Planted Ha | 1851.933 | 11850.9373

## Total Cost per Ha - Projected
Projected Total Cost Fully Planted
| 100% Planted | 75% Planted | 50% Planted |  | Est. YTD Spending | Annual Budget Remaining |  | 100% Planted | 75% Planted | 50% Planted
Ghana Annual Cost |  |  |  | Ghana | 707438.3947 | 611867.9332 | Ghana | 1319.3063 | 1677.2329 | 2326.288
Nursery Cost | 78367.2451 | 78367.2451 | 78367.2451 | Philippines | 652986.6476 | 867330.5352 | Philippines | 1475.0195 | 1427.667 | 1900.9732
Cap-Ex | 342468.4271 | 342468.4271 | 342468.4271
Infrastructure | 264236.372 | 264236.372 | 264236.372
Land Preparation | 194202.6712 | 171422.2194 | 120341.2779
Planting | 147035.981 | 115998.0113 | 79865.4051
Replanting | 6729.6331 | 5355.8742 | 3978.1474
Maintenance | 66337.0746 | 60147.6372 | 53958.1998
Fire & Security | 24209.194 | 24209.194 | 24209.194
Impact | 4483.6739 | 4483.6739 | 4483.6739
Administration | 191236.0558 | 191236.0558 | 191236.0558
Tax | 0 | 0 | 0
Total WAI Budget (USD) | 1319306.3279 | 1257924.71 | 1163143.9982
Ghana Per ha Cost | Cost /ha | Cost /ha | Cost /ha
Nursery Cost | 78.3672 | 104.4897 | 156.7345
Cap-Ex | 342.4684 | 456.6246 | 684.9369
Infrastructure | 264.2364 | 352.3152 | 528.4727
Land Preparation | 194.2027 | 228.563 | 240.6826
Planting | 147.036 | 154.664 | 159.7308
Replanting | 6.7296 | 7.1412 | 7.9563
Maintenance | 66.3371 | 80.1968 | 107.9164
Fire & Security | 24.2092 | 32.2789 | 48.4184
Impact | 4.4837 | 5.9782 | 8.9673
Administration | 191.2361 | 254.9814 | 382.4721
Tax | 0 | 0 | 0
Total WAII Budget (USD) | 1319.3063 | 1677.2329 | 2326.288
| 100% Planted | 75% Planted | 50% Planted
Philippines Annual Cost |  | Cost per Ha (USD) | Cost per Ha (USD)
Nursery Cost | 158541.7963 | 158541.7963 | 158541.7963
Cap-Ex | 247133.3333 | 247133.3333 | 247133.3333
Infrastructure | 95165.1467 | 95165.1467 | 95165.1467
Land Preparation | 390262.501 | 381922.7159 | 254615.1439
Planting | 185973.9607 | 169897.1971 | 134355.6543
Replanting | 0 | 0 | 0
Maintenance | 7433.9251 | 10714.2857 | 7142.8571
Fire & Security | 2939.996 | 5845.7143 | 3897.1429
Impact | 34289.5238 | 34289.5238 | 34289.5238
Administration | 398577 | 395540.6503 | 395540.6503
Tax | 0 | 0 | 0
Total Lanao Bamboo Budget (USD) | 1520317.1829 | 1499050.3635 | 1330681.2487
| TOTAL (USD) | Cost per Ha (USD) | Cost per Ha (USD)
Philippines per Ha Cost
Nursery Cost | 113.2441 | 150.9922 | 226.4883
Cap-Ex | 247.1333 | 235.3651 | 353.0476
Infrastructure | 95.1651 | 90.6335 | 135.9502
Land Preparation | 390.2625 | 363.7359 | 363.7359
Planting | 185.974 | 161.8069 | 191.9366
Replanting | 0 | 0 | 0
Maintenance | 7.4339 | 10.2041 | 10.2041
Fire & Security | 2.94 | 5.5673 | 5.5673
Impact | 34.2895 | 32.6567 | 48.985
Administration | 398.577 | 376.7054 | 565.0581
Tax | 0 | 0 | 0
Total Lanao Tree Budget (USD) | 1475.0195 | 1427.667 | 1900.9732

## % of Activities Completed
| Ghana | Lanao Bamboo
Slashing | 100% | 30%
Marking | 83% | 23%
Pitting | 83% | 5%
Broadcast spray | 51% | 3%
Planting | 38% | 4%
Post Planting Maintenance | 17% | 3%

## Avg Cost per Activity
| Ghana | Lanao Bamboo
Slashing | 49.67 | 75.79
Marking | 24.51 | 7.5
Pitting | 42.62 | 19.12
Broadcast spray | 21.95 | 14.24
Planting | 42.64 | 23.08
Post Planting Maintenance | 26.68 | 11.04
| 208.07 | 150.77

## Average Man Day per Activity
| Ghana | Lanao Bamboo
Slashing | 5.9 | 12.38
Marking | 2.8 | 1.23
Pitting | 4.87 | 3.12
Broadcast spray | 2.5 | 2.33
Planting | 4.86 | 3.77
Post Planting Maintenance | 3 | 1.8
| 23.93 | 24.63

## Man Days per Planted Ha
Man Days per Planted Ha
| Ghana | Lanao Bamboo
Cost per Planted Ha | 25.93 | 24.63
Farm Name | Total man day
Ghana | 25.93
Lanao Bamboo | 24.63

## Ghana
Comp. no. | Farm | Area (Ha) | Activity | Avg. Md/Ha | Total Md | Rate/Md | Total | Cost per Ha (GHS) | Cost per Ha (USD)
Compt 48 | Bandai Hills | 115 | Line Slashing | 3 | 345 | 51.15 | 17646.75 | 153.45 | 22.5662
Compt 48 | Bandai Hills | 16.7 | Line Slashing | 3 | 50.1 | 51.15 | 2562.615 | 153.45 | 22.5662
Compt 49 | Bandai Hills | 62 | Line Slashing | 3 | 186 | 51.15 | 9513.9 | 153.45 | 22.5662
Compt 49 | Bandai Hills | 42 | Line Slashing | 4 | 168 | 58.17 | 9772.56 | 232.68 | 34.2176
Compt 49 | Bandai Hills | 40 | Line Slashing | 4 | 160 | 58.17 | 9307.2 | 232.68 | 34.2176
Compt 106 | Bandai Hills | 45 | Slashing | 8 | 360 | 58.17 | 20941.2 | 465.36 | 68.4353
Compt 106 | Bandai Hills | 55 | Slashing | 8 | 440 | 58.17 | 25594.8 | 465.36 | 68.4353
Compt 119 | Bandai Hills | 52 | Slashing | 8 | 416 | 58.17 | 24198.72 | 465.36 | 68.4353
Compt 119 | Bandai Hills | 78.23 | Slashing | 8 | 625.84 | 58.17 | 36405.1128 | 465.36 | 68.4353
Compt 49 | Bandai Hills | 5.3 | Slashing | 8 | 42.4 | 58.17 | 2466.408 | 465.36 | 68.4353
Compt 16 | North Bandai | 112.6 | Line Slashing | 4 | 450.4 | 54.63 | 24605.352 | 218.52 | 32.1353
Compt 17 | North Bandai | 38.5 | Line Slashing | 4 | 154 | 54.63 | 8413.02 | 218.52 | 32.1353
Compt 17 | North Bandai | 40 | Line Slashing | 3 | 120 | 54.63 | 6555.6 | 163.89 | 24.1015
Compt 10 | North Bandai | 35 | Slashing | 6 | 210 | 45.17 | 9485.7 | 271.02 | 39.8559
Compt 10 | North Bandai | 70.2 | Slashing | 6 | 421.2 | 54.63 | 23010.156 | 327.78 | 48.2029
Compt 16 | North Bandai | 26 | Slashing | 8 | 208 | 61.63 | 12819.04 | 493.04 | 72.5059
Compt 17 | North Bandai | 28 | Slashing | 8 | 224 | 61.63 | 13805.12 | 493.04 | 72.5059
Compt 18 | North Bandai | 44.5 | Slashing | 8 | 356 | 54.63 | 19448.28 | 437.04 | 64.2706
Compt 19 | North Bandai | 61.8 | Slashing | 8 | 494.4 | 54.63 | 27009.072 | 437.04 | 64.2706
Compt 9 | North Bandai | 13 | Slashing | 6 | 78 | 54.63 | 4261.14 | 327.78 | 48.2029
Compt 9 | North Bandai | 115 | Slashing | 6 | 690 | 54.63 | 37694.7 | 327.78 | 48.2029
Compt 48 | Bandai Hills | 20 | Marking | 3 | 160 | 58.17 | 9307.2 | 174.51 | 25.6632
Compt 49 | Bandai Hills | 65 | Marking | 3 | 520 | 58.17 | 30248.4 | 174.51 | 25.6632
Compt 106 | Bandai Hills | 35 | Marking | 3 | 280 | 58.17 | 16287.6 | 174.51 | 25.6632
Compt 106 | Bandai Hills | 65 | Marking | 3 | 520 | 58.17 | 30248.4 | 174.51 | 25.6632
Compt 119 | Bandai Hills | 52.08 | Marking | 3 | 416.64 | 58.17 | 24235.9488 | 174.51 | 25.6632
Compt 119 | Bandai Hills | 78.15 | Marking | 3 | 625.2 | 58.17 | 36367.884 | 174.51 | 25.6632
Compt 48 | Bandai Hills | 37.2 | Marking | 3 | 297.6 | 58.17 | 17311.392 | 174.51 | 25.6632
Compt 48 | Bandai Hills | 84.8 | Marking | 3 | 678.4 | 58.17 | 39462.528 | 174.51 | 25.6632
Compt 10 | North Bandai | 57 | Marking | 1.5 | 313.5 | 61.63 | 19321.005 | 92.445 | 13.5949
Compt 17 | North Bandai | 96 | Marking | 3 | 768 | 61.63 | 47331.84 | 184.89 | 27.1897
Compt 19 | North Bandai | 56 | Marking | 3 | 448 | 61.63 | 27610.24 | 184.89 | 27.1897
Compt 16 | North Bandai | 70 | Marking | 3 | 560 | 61.63 | 34512.8 | 184.89 | 27.1897
Compt 16 | North Bandai | 31 | Marking | 3 | 248 | 61.63 | 15284.24 | 184.89 | 27.1897
Compt 18 | North Bandai | 40 | Marking | 3 | 320 | 61.63 | 19721.6 | 184.89 | 27.1897
Compt 9 | North Bandai | 41 | Marking | 1.5 | 225.5 | 58.17 | 13117.335 | 87.255 | 12.8316
Compt 48 | Bandai Hills | 20 | Pitting | 5 | 160 | 58.17 | 9307.2 | 290.85 | 42.7721
Compt 49 | Bandai Hills | 65 | Pitting | 5 | 520 | 58.17 | 30248.4 | 290.85 | 42.7721
Compt 106 | Bandai Hills | 35 | Pitting | 5 | 280 | 58.17 | 16287.6 | 290.85 | 42.7721
Compt 106 | Bandai Hills | 65 | Pitting | 5 | 520 | 58.17 | 30248.4 | 290.85 | 42.7721
Compt 119 | Bandai Hills | 52.08 | Pitting | 5 | 416.64 | 58.17 | 24235.9488 | 290.85 | 42.7721
Compt 119 | Bandai Hills | 78.15 | Pitting | 5 | 625.2 | 58.17 | 36367.884 | 290.85 | 42.7721
Compt 48 | Bandai Hills | 37.2 | Pitting | 5 | 297.6 | 58.17 | 17311.392 | 290.85 | 42.7721
Compt 48 | Bandai Hills | 84.8 | Pitting | 5 | 678.4 | 58.17 | 39462.528 | 290.85 | 42.7721
Compt 10 | North Bandai | 57 | Pitting | 4 | 313.5 | 61.63 | 19321.005 | 246.52 | 36.2529
Compt 17 | North Bandai | 96 | Pitting | 5 | 768 | 61.63 | 47331.84 | 308.15 | 45.3162
Compt 19 | North Bandai | 56 | Pitting | 5 | 448 | 61.63 | 27610.24 | 308.15 | 45.3162
Compt 16 | North Bandai | 70 | Pitting | 5 | 560 | 61.63 | 34512.8 | 308.15 | 45.3162
Compt 16 | North Bandai | 31 | Pitting | 5 | 248 | 61.63 | 15284.24 | 308.15 | 45.3162
Compt 18 | North Bandai | 40 | Pitting | 5 | 320 | 61.63 | 19721.6 | 308.15 | 45.3162
Compt 9 | North Bandai | 41 | Pitting | 4 | 225.5 | 58.17 | 13117.335 | 232.68 | 34.2176

## Philipines
Comp. no. | Farm | Area (Ha) | Activity | Avg. Md/Ha | Total Md | Rate/Md | Total | Cost per Ha (GHS) | Cost per Ha (USD)
| Lanao - Trees | 19.9 | Slashing | 9.397 | 187 | 319 | 59653 | 2997.6382 | 57.5362
| Lanao - Trees | 17.33 | Marking | 2.7121 | 47 | 319 | 14993 | 865.1471 | 16.6055
| Lanao - Trees | 14.52 | Pitting | 3.2493 | 47.18 | 319 | 15050.42 | 1036.5303 | 19.895
| Lanao - Trees | 15.15 | Planting | 2.5083 | 38 | 319 | 12122 | 800.132 | 15.3576
| Lanao - Trees | 34 | Planting (Seedling Hauling) | 1.0294 | 35 | 319 | 11165 | 328.3824 | 6.3029
| Lanao - Bamboo | 297.28 | Slashing | 12.3789 | 3680 | 319 | 1173920 | 3948.8698 | 75.794
| Lanao - Bamboo | 229.85 | Marking | 1.2251 | 281.6 | 319 | 89830.4 | 390.8218 | 7.5014
| Lanao - Bamboo | 47.61 | Pitting | 3.1233 | 148.7 | 319 | 47435.3 | 996.3306 | 19.1234
| Lanao - Bamboo | 26.7 | Broadcast spray | 2.3262 | 62.11 | 319 | 19813.09 | 742.0633 | 14.2431
| Lanao - Bamboo | 39.95 | Planting | 2.5282 | 101 | 319 | 32219 | 806.4831 | 15.4795
| Lanao - Bamboo | 58 | Planting (Seedling Hauling) | 1.2414 | 72 | 319 | 22968 | 396 | 7.6008
| Lanao - Bamboo | 27.74 | Post Planting Casing | 1.8025 | 50 | 319 | 15950 | 574.982 | 11.0361

## Cost per Man Day
Man Days per Planted Ha
| Ghana | Lanao Bamboo
Cost per Planted Ha | 4.32 | 5.67
Ghana | Total man day
Bandai Hills | 8.55
Lanao Bamboo | 6.12